## SLOC
Team Number: | 1
Week: | 7
Program Size (SLOC) | Actual
Base | 1417
Added | 3054
Deleted | 1042
Modified | 0
Reused | 0
From COTS | 0
Total New SLOC | 3429

## Progress
Progress Description:
Describe the progress on the project during the past week, both in qualitative and quantitative.
A. | List your top priority works that must be accomplished in this week
1 | Complete the front end part for notification system
2 | Complete the search engine integration
3 | Implement notification system on the backend using websocket.
4 | Complete the hot threads logic of thread page
5 | Implement unit test for the complete functionalities
6
7
8
B. | List dependencies or things/decision that you waiting for in this week
1 | Client feedback on the completed feature
2 | Thread categories from clients.
3 | Background image for login, registration, and about pages from clients.
4 | Logo of the system from clients.
5 | Content for about page from clients.
6 | Domain name to implement email related functionality.
C. | List your accomplishments from the previous week
1 | Almost complete Thread Page functionality except report thread, and integrate with notification system.
2 | Almost completed Profile Page except integrate with notification system
3 | DB update for category information
4 | Complete the category selection bar in the thread Page
5 | Complete the category selection in the profile Page
6
7
8
D. | Report your planned and actual man-hours for each category of your work in the previous week
| Effort (Hours) | Planned | Actual
| Operational Concept Development | 0 | 0
| System and Software Requirements Development | 0 | 36
| System and Software Architecture Development | 0 | 2
| Life Cycle Planning | 2 | 1
| Feasibility Evidence Description | 0 | 0
| Quality Management | 2 | 5
| Implementation | 80 | 40
| Testing | 16 | 16
| Project Administration | 6 | 6

## Risk
Top Project Risks as of 3/4/2015
Rank |  | Risk Description | Risk Mitigation Action Items | P(L) | S(L) | RE | No. of Weeks Active
This Week | Last Week
1 | 1 | Users may prefer existing systems with similar features | Make the WAT points system as an incentive to attract users over competitors. Advertize our system to USC and users. Create surveys and evaluate users' responses. | 6 | 9 | 54 | 10
2 | 4 | Search feature might become difficult and time-consuming, taking developer time off other features. | Research how this is done in other software. Try to find and implement existing solutions for our framework. | 5 | 8 | 40 | 2
3 | 2 | Might not have sufficient time to implement all features required to make the Q&A forum as good as existing solutions (e.g. Quora). | Prioritize features | 4 | 9 | 36 | 2
4 | 6 | Major update might happen for Laravel | We will stick with the current version if the update is not critical But if it is cirtical to our system then we can talk to our clients whether they need the update or not by provide pros and cons of the updating. | 3 | 6 | 18 | 8

## COTS
List of third-party components being considered for use in the system as of 2/4/2015
Component Name | Function of the component in the system | Related components |  | Component use in the system
|  | Dependency | Interaction | Black Box | White Box | Modify Code
MySQL | Data storage for the system |  | MySql driver to interact with Web-server | x
Apache | web-server for the system |  |  | x
Jquery | DOM manipulation | Javascript |  |  | x
Bootstrap | UI library (template system) | Javascript |  |  | x
Laravel | Framework | PHP |  |  | x
TinyMCE | HTML editor for users | Javascript |  |  | x
Components that were filtered in the previous week
Component Name | Rationale for filtering the component |  | Notes and References

## Defects, Problems, and Concerns
Defects, Problems, and Issues
Describe the defects, problems, and issues in the project during the past week
Avoidable Defects: a shortcoming, fault, imperfection or problem that could be prevented such as human error
Unavoidable Defects: a shortcoming, fault, imperfection or problem that the team has no control over such as a change in the requirement
Concern: A matter that might cause some trouble, worry or an unsettled matter is ready for a decision
A. List any avoidable defect occurred in the previous week
| Avoidable Defects | Proposed Solution
1 | During implementation there isn't adequate commenting for codes | Provide adequte comments for codes by assigning them with win conditions identifiers
2 | Lack of testing during the implementation and after they finished. | Take a look at TCP as a check list of what to test and do it properly.
3
4
5
B. List any unavoidable defect occurred in the previous week
| Unavoidable defect | Proposed Solution
1 | Due to work load of other courses, planned jobs could'nt be completed. | Every team member should review their schedule and take out time to complete their weekly assigned task for the course.
2 | The data presented on the website should not have copyright issues. | The team-members had approached the client with the issue, and still did not receive the material. This task has a dependency and can only be resolved once the client provide the content.
3
4
5
C. List any concern occurred in the previous week
| Concerns | Proposed Solution
1 | There were some files and entities not compatible with the Laravel convention. | Every team member should watch Laravel tutorial and stick to Laravel convention in order to maintain consistency.
2 | The team members were un-fimiliar of serch engines, and nobody have worked on one. | Each team member was told to read about search engine compatible with Laravel in free time and get some idea about its implementation.
3 | Some of the code use special laravel syntax so it is hard to count SLOC | Manually count SLOC of that part.
4
5