## SLOC
Team Number: | 1
Week: | 8
Program Size (SLOC) | Actual
Base | 0
Added | 0
Deleted | 0
Modified | 0
Reused | 0
From COTS | 0
Total New SLOC | 0

## Progress
Progress Description:
Describe the progress on the project during the past week, both in qualitative and quantitative.
A. | List your top priority works that must be accomplished in this week
1 | Plan on getting information from real user via surveys relating to the user-interface
2 | Review project documents
3 | Continue analyzing and evaluating NDIs which will we used in the project
4 | Continue developing system architecture
5 | Perform the Return of Investment analysis
6 | Plan and peform prototype presentation in class
7
8
B. | List dependencies or things/decision that you waiting for in this week
1 | Waiting for draft ROI analysis from client
2
3
4
5
C. | List your accomplishments from the previous week
1 | Evaluating some of the NDIs about programming languages and DBMS used to develop the project
2 | Finalize the Win-Win negotiations and complete the Win-Win negotiation report
3 | Present next version of WAT point prototype to client
4 | Start developing system architecture
5
6
7
8
D. | Report your planned and actual man-hours for each category of your work in the previous week
| Effort (Hours) | Planned | Actual
| Operational Concept Development | 14 | 12
| System and Software Requirements Development | 0 | 0
| System and Software Architecture Development | 16 | 10
| Life Cycle Planning | 9 | 8
| Feasibility Evidence Description | 30 | 32
| Quality Management | 4 | 12
| Implementation | 0 | 0
| Testing | 0 | 0
| Project Administration | 2 | 1

## Risk
Top Project Risks as of 10/27/2014
Rank |  | Risk Description | Risk Mitigation Action Items | P(L) | S(L) | RE | No. of Weeks Active
This Week | Last Week
1 | N/A | Users may existing prefer systems with similar features | Make the WAT points system stand out from competitors. Advertise our system to USC. Create surveys and evaluate users' response. | 7 | 10 | 70 | 0
2 | 3 | Users might not choose to use the system even if all the specifications are met by the system | We need to have certain level of discussion with the actual users as to whether they are willing to learn and use the new system. Risk mitigated by interaction with potential future users via discussions and surveys | 7 | 10 | 70 | 8
3 | 2 | Lack of Involvement by success-critical-stakeholders:Do not understand clearly enough the success-critical Stakeholder positions | Further understanding of needs and system scoping is needed | 5 | 10 | 50 | 8
4 | 1 | Undefined Plan and Requirements: The requirements of the system are not solid, and are just partly known. Requirement have a tendency to change with project development. | Consult with the clients to find more details about the unclear features, develop the prototype or graph to clarify the features, and discuss about the potential system flaws | 5 | 9 | 45 | 8
5 | N/A | May not have sufficient time to create comprehensive prototypes for important parts of the system | Prioritize the prototyping. Use minimum effort for each prototype to gain enough information to see the feature is feasible. | 7 | 6 | 42 | 0
6 | N/A | User survey may have flaws and not yield correct information about user experience. | Consult our clients and collaboratively develop a good user survey. | 5 | 7 | 35 | 0
7 | 4 | Architecture/Reuse/Non-Development Item conflict: There is no current server available for our system. The COTS/NDI used are poorly matched. A database system may be needed in order to keep the accounts, logs and forum informations | Looking for services provided only and analyze all options if they are suitable to our conditions. Establish off-line server for using as a prototype for the clients manages to overcome the problem of interoperatibility | 4 | 8 | 32 | 8

## COTS
List of third-party components being considered for use in the system as of 10/27/2014
Component Name | Function of the component in the system | Related components |  | Component use in the system
|  | Dependency | Interaction | Black Box | White Box | Modify Code
MySQL | Data storage for the system |  | MySql driver to interact with Web-server | x
Apache | web-server for the system |  |  | x
Joomla | CMS | PHP |  |  |  | x
Jquery | DOM manipulation | Javascript |  |  | x
Bootstrap | UI library (template system) | Javascript |  |  | x
Wordpress | CMS | PHP |  |  |  | x
Components that were filtered in the previous week
Component Name | Rationale for filtering the component |  | Notes and References
PostgreSQL | NDI Component Rating |  | See FED V2.1
SQLlite | NDI Component Rating |  | See FED V2.1
Oracle | NDI Component Rating |  | See FED V2.1
Microsoft SQL Server | NDI Component Rating |  | See FED V2.1
DB2 | NDI Component Rating |  | See FED V2.1
SQLite | NDI Component Rating |  | See FED V2.1

## Defects, Problems, and Concerns
Defects, Problems, and Issues
Describe the defects, problems, and issues in the project during the past week
Avoidable Defects: a shortcoming, fault, imperfection or problem that could be prevented such as human error
Unavoidable Defects: a shortcoming, fault, imperfection or problem that the team has no control over such as a change in the requirement
Concern: A matter that might cause some trouble, worry or an unsettled matter is ready for a decision
A. List any avoidable defect occurred in the previous week
| Avoidable Defects | Proposed Solution
1 | The document should cover analysis for 2 semester and not be constrained for 1 semester | The document were updated to include specific data
2 | The ARB presentation was not posted on the website | Update the website early
3 | Develop the business case analysis | The clients were asked to come up with the ROI plan
4 | Late detection of inconsistency of the documents | Check the documents carefully ealier
5
B. List any unavoidable defect occurred in the previous week
| Unavoidable defect | Proposed Solution
1 | There may not be enough time to create prototypes due to generic features | Prioritize the prototypes and try using minimal effort for each prototype.
2 | Some of the requirements are still uncertain | Schedule another meeting with the clients and discuss uncertain requirements
3
4
5
C. List any concern occurred in the previous week
| Concerns | Proposed Solution
1 | Think about the test-cases for the test case analysis that needs to be presented at the end of semester | The team has start to work on the test-cases fo the WAT system
2 | Campusbubble.com is a similar system for USC students | Investigate which features users would like in such a system
3 | The user-interface prototype might not be accepted by the user | Get real user feedback via surveys
4 | The LOS stated in the document is hard to measure | Discuss about this issue with our client. Document the LOS that can be quantified
5