## SLOC
Team Number: | 1
Week: | 11
Program Size (SLOC) | Actual
Base | 3967
Added | 1308
Deleted | 241
Modified | 0
Reused | 0
From COTS | 0
Total New SLOC | 5034

## Progress
Progress Description:
Describe the progress on the project during the past week, both in qualitative and quantitative.
A. | List your top priority works that must be accomplished in this week
1 | Finalize the front end part for notification system
2 | Create the admin page
3 | Implement unit test for the complete functionalities
4 | Implement the changes requested from client about profile page
5 | Allow some potential user to test and use the system
6 | Complete 90% of the system implementation.
7 | Implement a search result page to show more search result details
8
B. | List dependencies or things/decision that you waiting for in this week
1 | List of names of levels used in WAT point system from client
2 | Thread categories from clients.
3 | Background image for login, registration, and about pages from clients.
4 | Logo of the system from clients.
5 | Content for "about page" from clients.
6 | Domain name to implement email related functionality.
C. | List your accomplishments from the previous week
1 | Complete the hot threads logic of thread page
2 | Modify the home page layout
3 | Modify the profile UI
4 | Decide on notification system logical schema
5 | Fix the bugs and finish the new requirements from CCD
6 | Implement an Event page
7
D. | Report your planned and actual man-hours for each category of your work in the previous week
| Effort (Hours) | Planned | Actual
| Operational Concept Development | 0 | 4
| System and Software Requirements Development | 12 | 20
| System and Software Architecture Development | 0 | 0
| Life Cycle Planning | 0 | 2
| Feasibility Evidence Description | 0 | 0
| Quality Management | 4 | 10
| Implementation | 70 | 160
| Testing | 16 | 16
| Project Administration | 4 | 6

## Risk
Top Project Risks as of 3/18/2015
Rank |  | Risk Description | Risk Mitigation Action Items | P(L) | S(L) | RE | No. of Weeks Active
This Week | Last Week
1 | 1 | Users may prefer existing systems with similar features | Make the WAT points system as an incentive to attract users over competitors. Advertize our system to USC and users. Create surveys and evaluate users' responses. | 5 | 9 | 45 | 14
2 | N/A | The server that will be selected to host the application may encounter a performance problem as it needs to host application developed with PHP, Node.js, Redis, and Elasticsearch. | Perform testing to optimize the application and evaluate potential server candidates to suggest the clients. | 6 | 5 | 30 | 0
3 | 4 | Major update might happen for Laravel | We will stick with the current version if the update is not critical But if it is cirtical to our system then we can talk to our clients whether they need the update or not by provide pros and cons of the updating. | 3 | 6 | 18 | 12

## COTS
List of third-party components being considered for use in the system as of 2/4/2015
Component Name | Function of the component in the system | Related components |  | Component use in the system
|  | Dependency | Interaction | Black Box | White Box | Modify Code
MySQL | Data storage for the system |  | MySql driver to interact with Web-server | x
Apache | web-server for the system |  |  | x
Jquery | DOM manipulation | Javascript |  |  | x
Bootstrap | UI library (template system) | Javascript |  |  | x
Laravel | Framework | PHP |  |  | x
TinyMCE | HTML editor for users | Javascript |  |  | x
Elasticsearch | Search system | JVM | Elasticsearch API for PHP | x
PhpUnit | Unit Test | PHP | Test the function | x
Websocket | Real-time communication between front-end and back-end | Javascript | as Node.Js Module | x
NodeJS | Javascript Server/ send data firing from back-end (in redis) and send them to the front-end by utilizing websocket module | Javascript | with Websocket and Redis | x
Redis | Receive event firing from the backend / Key-value |  | with Node.js and Websocket | x
FullCalendar | Event Plugin | Javascript, Jquery |  |  | x
Components that were filtered in the previous week
Component Name | Rationale for filtering the component |  | Notes and References

## Defects, Problems, and Concerns
Defects, Problems, and Issues
Describe the defects, problems, and issues in the project during the past week
Avoidable Defects: a shortcoming, fault, imperfection or problem that could be prevented such as human error
Unavoidable Defects: a shortcoming, fault, imperfection or problem that the team has no control over such as a change in the requirement
Concern: A matter that might cause some trouble, worry or an unsettled matter is ready for a decision
A. List any avoidable defect occurred in the previous week
| Avoidable Defects | Proposed Solution
1 | The server stopped working when clients were testing the system during one of the client meetin | Check the server prior showing the product to the clients
2 | The HTML code written by developers had a number of syntax errors. | All developers will have a responsibility to check their codes with an online tool (W3C Markup Validation Service)
3 | Some of the team members wait until the last minute before asking for help when they stuck. This puts pressure on the entire team as the deadline draws near. | The team-member who require help should inform the team when they have trouble to get the necessary help in the weekly meeting or on group chat which the team will know and be able to help solving the problems.
4
5
B. List any unavoidable defect occurred in the previous week
| Unavoidable defect | Proposed Solution
1 | Due to work load of other courses, planned jobs could'nt be completed. | Every team member should review their schedule and take out time to complete their weekly assigned task for the course.
2 | The data presented on the website should not have copyright issues. | The clients asked to remove all the things that have copyright issue. For now, they have asked us to use simple color combination rather than images for the website until they can provide all needed materials.
3 | The clients keep asking for modification to UI in each meeting. This process of revising the design is time consuming and involves redoing the work. | The developers should consult the client when they decide to make any changes to the UI designs and reach solid conclusion agreed by both clients and the team.
4
5
C. List any concern occurred in the previous week
| Concerns | Proposed Solution
1 | It became difficult to syncronize with the front-end and back-end due to partition of work. | Each team member should be aware of each other work and be able help other team-members when they need.
2 | Some of the code use special laravel syntax so it is hard to count SLOC | Manually count SLOC of that part.
3
4
5