## SLOC
Team Number: | 1
Week: | 6
Program Size (SLOC) | Actual
Base | 0
Added | 0
Deleted | 0
Modified | 0
Reused | 0
From COTS | 0
Total New SLOC | 0

## Progress
Progress Description:
Describe the progress on the project during the past week, both in qualitative and quantitative.
A. | List your top priority works that must be accomplished in this week
1 | Finalize the Win-Win negotiations and complete the Win-Win negotiation report
2 | Plan on getting information from real user
3 | Present next version WAT prototype to client
4 | Decide which NDI will we use to develop the project
5 | Continute evaluating the NDI used to develop the project
6
7
8
B. | List dependencies or things/decision that you waiting for in this week
1 | Waiting for feedback regarding the WAT point prototype#2
2 | Waiting for feedback regarding the new GUI prototype of the project
3
4
5
C. | List your accomplishments from the previous week
1 | Created new WAT point prototype according to the feedback got form clients
2 | Create new GUI prototype accroding to the feedback from our clients
3 | Created Draft Foundation Commitment Package
4 | Evaluated effort needed in developing the project with COINCOMO
5 | Present ARB and FCR
6 | Analyze CMS NDI
7
8
D. | Report your planned and actual man-hours for each category of your work in the previous week
| Effort (Hours) | Planned | Actual
| Operational Concept Development | 12 | 8
| System and Software Requirements Development | 15 | 20
| System and Software Architecture Development | 8 | 8
| Life Cycle Planning | 24 | 20
| Feasibility Evidence Description | 55 | 65
| Quality Management | 4 | 4
| Implementation | 4 | 6
| Testing | 0 | 0
| Project Administration | 4 | 5

## Risk
Top Project Risks as of 10/01/2014
Rank |  | Risk Description | Risk Mitigation Action Items | P(L) | S(L) | RE | No. of Weeks Active
This Week | Last Week
1 | 1 | Undefined Plan and Requirements: The requirements of the system are not solid, and are just partly known. Requirement have a tendency to change with project development. | Consult with the clients to find more details about the unclear features, develop the prototype or graph to clarify the features, and discuss about the potential system flaws | 8 | 9 | 72 | 6
2 | 4 | Lack of Invovement by success-critical-stakeholders:Do not understand clearly enough the success-critical Stakeholder positions | Further understanding of needs and system scoping is needed | 5 | 10 | 50 | 6
3 | 2 | User Risk: users may not accept to use the system even if all the specification are met by the system | We need to have certain level of discussion with the actual users as to whether they are willing to learn and use the new system we are developing | 5 | 10 | 50 | 6
4 | 7 | Architecture/Reuse/Non-Development Item conflict: There is no current server available for our system. The COTS/NDI used are poorly matched. A database system may be needed in order to keep the accounts, logs and forum informations | Looking for services provided only and analyze all options if they are suitable to our conditions. Establish off-line server for using as a prototype for the clients manages to overcome the problem of interoperatibility | 5 | 8 | 40 | 6
5 | 6 | Client's availability: He is extremely busy. Schedule a meeting during class schedule might not be possible | Forsee meetings in advance and acquire cilent's schedule. If there will be a meeting, the team will notify the clients early to allocate the time slot. | 5 | 8 | 40 | 6
6 | N/A | Human-System integration shortfalls: We do not have human factors expertise and need to come up with the user-friendly interface | Prioritize all features and develop the most needed features first | 5 | 7 | 35 | 0
7 | 3 | Scope and Time constraint: The scope of this project is very large. There are many components that need to be considered. To include all functionalities client mentioned within this time constraint might not be possible | Prioritize all features and develop the most needed features first | 7 | 3 | 21 | 6
8 | N/A | Human Resources and Contractors: Reaching the current USC data, level of permission to access his details and give points based on his achievements | Re-prioritize features if this issue occures | 4 | 2 | 8 | 0
9 | N/A
10 | N/A

## COTS
List of third-party components being considered for use in the system as of 10/01/2014
Component Name | Function of the component in the system | Related components |  | Component use in the system
|  | Dependency | Interaction | Black Box | White Box | Modify Code
MySQL | Data storage for the system |  | MySql driver to interact with Web-server | x
Apache | web-server for the system |  |  | x
Drupal | CMS | PHP |  |  |  | x
Joomla | CMS | PHP |  |  |  | x
Wordpress | CMS | PHP |  |  |  | x
Jquery | DOM manipulation | Javascript |  |  | x
Bootstrap | UI library (template system) | Javascript |  |  | x
Components that were filtered in the previous week
Component Name | Rationale for filtering the component |  | Notes and References
Drupal | Based NDI to use in the project |  | look at FED file

## Defects, Problems, and Concerns
Defects, Problems, and Issues
Describe the defects, problems, and issues in the project during the past week
Avoidable Defects: a shortcoming, fault, imperfection or problem that could be prevented such as human error
Unavoidable Defects: a shortcoming, fault, imperfection or problem that the team has no control over such as a change in the requirement
Concern: A matter that might cause some trouble, worry or an unsettled matter is ready for a decision
A. List any avoidable defect occurred in the previous week
| Avoidable Defects | Proposed Solution
1 | Problem with ARB negotitation time slot | We dicuss avaialble time with clients and reserve the time slot early
2 | The previous prototype reagarding the WAT point system was not fully fulfilled the requriments from the clients | We came up with a new strategy to handle problem in WAT point system and create a new prototype accordingly
3
4
5
B. List any unavoidable defect occurred in the previous week
| Unavoidable defect | Proposed Solution
1 | There are no enough prototypes to demonstrate all the features to the clients | Develop more prototypes to provide understandings among team and clients
2 | Some of the requirements are still uncertain | Schedule another meeting with the clients and discuss further about the requirement
3 | Inefficient time management | plan further ahead
4
5
C. List any concern occurred in the previous week
| Concerns | Proposed Solution
1 | A new startegy to handle the WAT point system proposed may not be sattisfied by the clients | Develop prototypes to explain new strategy to the clients and obtain feedback
2 | There is no specific requirements for the UI | Find out whether we can design it freely and how we should design it by consulting with the clients
3 | There is no budget | Analyze more options that will not cost the team money, such as open souce software and free hostings
4
5