## SLOC
Team Number: | 1
Week: | 14
Program Size (SLOC) | Actual
Base | 318
Added | 0
Deleted | 0
Modified | 0
Reused | 0
From COTS | 0
Total New SLOC | 0

## Progress
Progress Description:
Describe the progress on the project during the past week, both in qualitative and quantitative.
A. | List your top priority works that must be accomplished in this week
1 | Review artifacts and make necessary changes according to TA feedback
2 | Set up hosting server
3 | Work on feasibility evidence for RDCR ARB
4 | Seperate individual weekly tasks and assign people in charge
5 | Start developing the website
6 | Create detailed test and project plan
7 | Keep clients in loop, and inform them about team progress weekly
8
B. | List dependencies or things/decision that you waiting for in this week
1 | Check if we can use AWS server, for A2 above.
2
3
4
5
C. | List your accomplishments from the previous week
1 | Assigned team roles, responsibilities for current semester
2 | Set fixed meeting time for every week.
3
4
5
6
7
8
D. | Report your planned and actual man-hours for each category of your work in the previous week
| Effort (Hours) | Planned | Actual
| Operational Concept Development | 0 | 0
| System and Software Requirements Development | 0 | 0
| System and Software Architecture Development | 0 | 0
| Life Cycle Planning | 0 | 0
| Feasibility Evidence Description | 0 | 0
| Quality Management | 0 | 0
| Implementation | 0 | 0
| Testing | 0 | 0
| Project Administration | 16 | 16

## Risk
Top Project Risks as of 19/01/2015
Rank |  | Risk Description | Risk Mitigation Action Items | P(L) | S(L) | RE | No. of Weeks Active
This Week | Last Week
1 | 1 | Users may prefer existing systems with similar features | - Make the WAT points system as an incentive to attract users over competitors. Advertize our system to USC and users. Create surveys and evaluate users' responses. | 6 | 9 | 54 | 4
2 | 2 | System might not add sufficient benefits for users to join. | - We conduct the survey to acquire users' feedback regarding the project. - We will create the user interface mock up to acquire feedback from the clients | 5 | 9 | 45 | 12
3 | 5 | Undefined Plan and Requirements: - The scope of the campaign functionality is not finalized - The requirement about the UI of the system is not finalized - The point system is still not verified by potential users - The scope of the search functionality is not certain Requirement have a tendency to change with project development. | - Consult with the clients how campaign functionality works - Prototyping will help us know more about point systems, search functionality, and UI - Get the feedback of surveys for UI | 5 | 9 | 45 | 12
4 | N/A | Major update might happen for Laravel | - We will stick with the current version if the update is not critical But if it is cirtical to our system then we can talk to our clients whether they need the update or not by provide pros and cons of the updating. | 3 | 6 | 18 | 1

## COTS
List of third-party components being considered for use in the system as of 11/26/2014
Component Name | Function of the component in the system | Related components |  | Component use in the system
|  | Dependency | Interaction | Black Box | White Box | Modify Code
MySQL | Data storage for the system |  | MySql driver to interact with Web-server | x
Apache | web-server for the system |  |  | x
Jquery | DOM manipulation | Javascript |  |  | x
Bootstrap | UI library (template system) | Javascript |  |  | x
Laravel | Framework | PHP |  |  | x
Components that were filtered in the previous week
Component Name | Rationale for filtering the component |  | Notes and References

## Defects, Problems, and Concerns
Defects, Problems, and Issues
Describe the defects, problems, and issues in the project during the past week
Avoidable Defects: a shortcoming, fault, imperfection or problem that could be prevented such as human error
Unavoidable Defects: a shortcoming, fault, imperfection or problem that the team has no control over such as a change in the requirement
Concern: A matter that might cause some trouble, worry or an unsettled matter is ready for a decision
A. List any avoidable defect occurred in the previous week
| Avoidable Defects | Proposed Solution
1 | All team members did not study the new framework Laravel | Every team member should be commited, and complete the tutorial.
2 | Hard to schedule meetings due to time conflicts this semester. | Find a time when all team members are available to meet weekly.
3
4
5
B. List any unavoidable defect occurred in the previous week
| Unavoidable defect | Proposed Solution
1
2
3
4
5
C. List any concern occurred in the previous week
| Concerns | Proposed Solution
1 | Find a suitable free hosting service. | Compare different alternatives.
2 | The selected hosting service may not have enough resources. | Find a new web hosting or pay for more resources.
3
4
5