## SLOC
Team Number: | 1
Week: | 9
Program Size (SLOC) | Actual
Base | 3429
Added | 670
Deleted | 132
Modified | 0
Reused | 0
From COTS | 0
Total New SLOC | 3967

## Progress
Progress Description:
Describe the progress on the project during the past week, both in qualitative and quantitative.
A. | List your top priority works that must be accomplished in this week
1 | Finalize the front end part for notification system
2 | Further prototypes and implement search functionality integrating with front-end
3 | Implement notification system on the backend using websocket.
4 | Implement unit test for the complete functionalities
5
6
7
8
B. | List dependencies or things/decision that you waiting for in this week
1 | Client feedback on the completed feature
2 | Thread categories from clients.
3 | Background image for login, registration, and about pages from clients.
4 | Logo of the system from clients.
5 | Content for "about page" from clients.
6 | Domain name to implement email related functionality.
C. | List your accomplishments from the previous week
1 | Complete the hot threads logic of thread page
2 | Study how to integrate Elasticsearch into our system
3 | Implment prototype for search functionality (back-end)
4 | Decide on notification system logical schema
5 | Implement search suggestion in the navigation bar (front-end)
6 | Increase thread&post robustness
7
8
D. | Report your planned and actual man-hours for each category of your work in the previous week
| Effort (Hours) | Planned | Actual
| Operational Concept Development | 0 | 0
| System and Software Requirements Development | 6 | 9
| System and Software Architecture Development | 3 | 5
| Life Cycle Planning | 0 | 0
| Feasibility Evidence Description | 8 | 10
| Quality Management | 2 | 0
| Implementation | 28 | 20
| Testing | 10 | 6
| Project Administration | 1 | 1

## Risk
Top Project Risks as of 3/18/2015
Rank |  | Risk Description | Risk Mitigation Action Items | P(L) | S(L) | RE | No. of Weeks Active
This Week | Last Week
1 | 1 | Users may prefer existing systems with similar features | Make the WAT points system as an incentive to attract users over competitors. Advertize our system to USC and users. Create surveys and evaluate users' responses. | 6 | 9 | 54 | 12
2 | 3 | Might not have sufficient time to implement all features required to make the Q&A forum as good as existing solutions (e.g. Quora). | Prioritize features | 4 | 9 | 36 | 4
3 | 2 | Elasticsearch that the team choose to apply in the project may cause a problem in maintainance as it requires the team to run search server concurrently with the application server and the data used in the wat system need maintaining between the two servers. | Research how this is done in other software practices. Try to find the implementation methods suitable for the project. | 4 | 6 | 24 | 4
4 | 4 | Major update might happen for Laravel | We will stick with the current version if the update is not critical But if it is cirtical to our system then we can talk to our clients whether they need the update or not by provide pros and cons of the updating. | 3 | 6 | 18 | 10

## COTS
List of third-party components being considered for use in the system as of 2/4/2015
Component Name | Function of the component in the system | Related components |  | Component use in the system
|  | Dependency | Interaction | Black Box | White Box | Modify Code
MySQL | Data storage for the system |  | MySql driver to interact with Web-server | x
Apache | web-server for the system |  |  | x
Jquery | DOM manipulation | Javascript |  |  | x
Bootstrap | UI library (template system) | Javascript |  |  | x
Laravel | Framework | PHP |  |  | x
TinyMCE | HTML editor for users | Javascript |  |  | x
Elasticsearch | Search system | JVM | Elasticsearch API for PHP | x
PhpUnit | Unit Test | PHP | Test the function | x
Websocket | Real-time communication between front-end and back-end | Javascript | as Node.Js Module | x
NodeJS | Javascript Server/ send data firing from back-end (in redis) and send them to the front-end by utilizing websocket module | Javascript | with Websocket and Redis | x
Redis | Receive event firing from the backend / Key-value |  | with Node.js and Websocket | x
Components that were filtered in the previous week
Component Name | Rationale for filtering the component |  | Notes and References

## Defects, Problems, and Concerns
Defects, Problems, and Issues
Describe the defects, problems, and issues in the project during the past week
Avoidable Defects: a shortcoming, fault, imperfection or problem that could be prevented such as human error
Unavoidable Defects: a shortcoming, fault, imperfection or problem that the team has no control over such as a change in the requirement
Concern: A matter that might cause some trouble, worry or an unsettled matter is ready for a decision
A. List any avoidable defect occurred in the previous week
| Avoidable Defects | Proposed Solution
1 | Some features were thought were easy to work on, but turned out to be complex while implementation. | Each team-member were involved in implementing the complex task and get it done, rather than having individual responsible for the task.
2 | It was time consuming to convert some files and entitites compatible with Laravel convention. | Each team-member were asked to follow the convention from the beginning to avoid re-work and time cost.
3
4
5
B. List any unavoidable defect occurred in the previous week
| Unavoidable defect | Proposed Solution
1 | Due to work load of other courses, planned jobs could'nt be completed. | Every team member should review their schedule and take out time to complete their weekly assigned task for the course.
2 | The data presented on the website should not have copyright issues. | The team-members had approached the client with the issue, and still did not receive the materials. This task has a dependency and can only be resolved once the client provide the contents.
3 | Team was unable to schedule a necessary meeting with the clients due to their busy schedule. | The team planned Hangout session with the clients on their preferable time.
4
5
C. List any concern occurred in the previous week
| Concerns | Proposed Solution
1 | There was no update from one of the team member as to whether they have started with the assigned task or is near to completion. | The team member was continously approached by the team. And the team was able to receive an update.
2 | Some of the code use special laravel syntax so it is hard to count SLOC | Manually count SLOC of that part.
3
4
5