## SLOC
Team Number: | 1
Week: | 5
Program Size (SLOC) | Actual
Base | 696
Added | 1417
Deleted | 0
Modified | 0
Reused | 0
From COTS | 0
Total New SLOC | 2113

## Progress
Progress Description:
Describe the progress on the project during the past week, both in qualitative and quantitative.
A. | List your top priority works that must be accomplished in this week
1 | Complete the design of Notification Page as per Laravel format
2 | Complete the design of Thread Page as per Laravel format
3 | Complete the design of Profile Page as per Laravel format
4 | Complete the design of NAvigation Bar as per Laravel format
5 | DB update for category information
6 | Complete the category selection bar as per Laravel format
7
8
B. | List dependencies or things/decision that you waiting for in this week
1 | Client feedback on new/updated requirements
2 | Code review on weekly meeting
3
4
5
C. | List your accomplishments from the previous week
1 | Review artifacts and make necessary changes according to TA feedback RDCR ARB
2 | Create detailed test and project plan
3 | Complete the design of Login Page as per Laravel format
4 | Keep clients in loop, and inform them about team progress bi-weekly
5 | Work on feasibility evidence for RDCR ARB (formalize requirements)
6 | Implementation of point system, registration, login, thread creation,update, deletion
7 | Get tutored about unit testing
8 | Complete the design of Registration Page as per Laravel format
D. | Report your planned and actual man-hours for each category of your work in the previous week
| Effort (Hours) | Planned | Actual
| Operational Concept Development | 0 | 0
| System and Software Requirements Development | 16 | 42
| System and Software Architecture Development | 0 | 0
| Life Cycle Planning | 16 | 10
| Feasibility Evidence Description | 0 | 0
| Quality Management | 4 | 5
| Implementation | 50 | 62
| Testing | 8 | 10
| Project Administration | 2 | 2

## Risk
Top Project Risks as of 2/4/2015
Rank |  | Risk Description | Risk Mitigation Action Items | P(L) | S(L) | RE | No. of Weeks Active
This Week | Last Week
1 | 1 | Users may prefer existing systems with similar features | - Make the WAT points system as an incentive to attract users over competitors. Advertize our system to USC and users. Create surveys and evaluate users' responses. | 6 | 9 | 54 | 8
2 | N/A | Might not have sufficient time to implement all features required to make the Q&A forum as good as existing solutions (e.g. Quora). | Prioritize features | 6 | 9 | 54 | 0
3 | 2 | System might not add sufficient benefits for users to join. | - We conduct the survey to acquire users' feedback regarding the project. - We will create the user interface mock up to acquire feedback from the clients | 5 | 9 | 45 | 16
4 | N/A | Search feature might become difficult and time-consuming, taking developer time off other features. | Research how this is done in other software. Try to find and implement existing solutions for our framework. | 5 | 8 | 40 | 0
5 | N/A | Lack of client involvement: client might not be able to sufficiently review developers' interpretations of high-level features, which might cause a gap between client expectations and actual implementation. | Give the client access to the system so that features can be tested as they are developed and get feedback from them | 4 | 7 | 28 | 0
6 | 4 | Major update might happen for Laravel | - We will stick with the current version if the update is not critical But if it is cirtical to our system then we can talk to our clients whether they need the update or not by provide pros and cons of the updating. | 3 | 6 | 18 | 5

## COTS
List of third-party components being considered for use in the system as of 2/4/2015
Component Name | Function of the component in the system | Related components |  | Component use in the system
|  | Dependency | Interaction | Black Box | White Box | Modify Code
MySQL | Data storage for the system |  | MySql driver to interact with Web-server | x
Apache | web-server for the system |  |  | x
Jquery | DOM manipulation | Javascript |  |  | x
Bootstrap | UI library (template system) | Javascript |  |  | x
Laravel | Framework | PHP |  |  | x
TinyMCE | HTML editor for users | Javascript |  |  | x
Components that were filtered in the previous week
Component Name | Rationale for filtering the component |  | Notes and References

## Defects, Problems, and Concerns
Defects, Problems, and Issues
Describe the defects, problems, and issues in the project during the past week
Avoidable Defects: a shortcoming, fault, imperfection or problem that could be prevented such as human error
Unavoidable Defects: a shortcoming, fault, imperfection or problem that the team has no control over such as a change in the requirement
Concern: A matter that might cause some trouble, worry or an unsettled matter is ready for a decision
A. List any avoidable defect occurred in the previous week
| Avoidable Defects | Proposed Solution
1 | Keep the project schedule, and individual member semester load in mind and think appropriately about the development. | Due to time constraint, map development with the requirment priorities documented in windbook.
2 | Updated document files were not posted on website before the RDCR. | Keep the website updated and upload the updated documents on the website before the presentation
3 | Use meaningful data for the prototype. | Update the database fields data to give real feel of the application at the time of presentation.
4 | Focus more on implementing important feature. | Map development with Win condition priorities.
5
B. List any unavoidable defect occurred in the previous week
| Unavoidable defect | Proposed Solution
1 | Due to work load of other courses, planned jobs could'nt be completed. | Every team member should review their schedule and take out time to complete their weekly assigned task for the ocurse.
2
3
4
5
C. List any concern occurred in the previous week
| Concerns | Proposed Solution
1 | There were some files and entities not compatible with the Laravel convention. | Every team member should watch Laravel tutorial and stick to Laravel convention in order to maintain consistency.
2 | The project scope seems bigger than the estimated time. | Sit with clients, negotiate and limit the system feature based on requirement prioritites.
3 | The ARB recommends us to formalize and detail our requirements. | We should look at some other Forums site like Quora to get detailed examples and inspirtions and use them to adapt to the project
4
5