## SLOC
Team Number: | 1
Week: | 15
Program Size (SLOC) | Actual
Base | 5838
Added | 641
Deleted | 64
Modified | 0
Reused | 0
From COTS | 0
Total New SLOC | 6415

## Progress
Progress Description:
Describe the progress on the project during the past week, both in qualitative and quantitative.
A. | List your top priority works that must be accomplished in this week
1 | Transfer the system to clients
2 | Plan and deploy the sytem into new server provided by clients
3 | Test the system on the new server
4 | Prepare mateirials and train clients
5 | Fix some bugs
6
7
8
B. | List dependencies or things/decision that you waiting for in this week
1 | List of names of levels used in WAT point system from clients
2 | Thread categories from clients.
3 | Logo of the system from clients.
4 | Content for "about page" from clients.
5 | Selected hosting services
6
C. | List your accomplishments from the previous week
1 | Implement unit test for the complete functionalities
2 | Code review fixes
3 | Complete all related documents
4
5
6
7
D. | Report your planned and actual man-hours for each category of your work in the previous week
| Effort (Hours) | Planned | Actual
| Operational Concept Development | 0 | 0
| System and Software Requirements Development | 0 | 0
| System and Software Architecture Development | 0 | 0
| Life Cycle Planning | 0 | 0
| Feasibility Evidence Description | 0 | 0
| Quality Management | 10 | 5
| Implementation | 30 | 64
| Testing | 50 | 26
| Project Administration | 8 | 6

## Risk
Top Project Risks as of 3/18/2015
Rank |  | Risk Description | Risk Mitigation Action Items | P(L) | S(L) | RE | No. of Weeks Active
This Week | Last Week
1 | 1 | Users may prefer existing systems with similar features | Make the WAT points system as an incentive to attract users over competitors. Advertize our system to USC and users. Create surveys and evaluate users' responses. | 4 | 8 | 32 | 18
2 | 2 | The server that will be selected to host the application may encounter a performance problem as it needs to host application developed with PHP, Node.js, Redis, and Elasticsearch. | Perform testing to optimize the application and evaluate potential server candidates to suggest the clients. | 5 | 5 | 25 | 4

## COTS
List of third-party components being considered for use in the system as of 2/4/2015
Component Name | Function of the component in the system | Related components |  | Component use in the system
|  | Dependency | Interaction | Black Box | White Box | Modify Code
MySQL | Data storage for the system |  | MySql driver to interact with Web-server | x
Apache | web-server for the system |  |  | x
Jquery | DOM manipulation | Javascript |  |  | x
Bootstrap | UI library (template system) | Javascript |  |  | x
Laravel | Framework | PHP |  |  | x
TinyMCE | HTML editor for users | Javascript |  |  | x
Elasticsearch | Search system | JVM | Elasticsearch API for PHP | x
PhpUnit | Unit Test | PHP | Test the function | x
Websocket | Real-time communication between front-end and back-end | Javascript | as Node.Js Module | x
NodeJS | Javascript Server/ send data firing from back-end (in redis) and send them to the front-end by utilizing websocket module | Javascript | with Websocket and Redis | x
Redis | Receive event firing from the backend / Key-value |  | with Node.js and Websocket | x
FullCalendar | Event Plugin | Javascript, Jquery |  |  | x
Components that were filtered in the previous week
Component Name | Rationale for filtering the component |  | Notes and References

## Defects, Problems, and Concerns
Defects, Problems, and Issues
Describe the defects, problems, and issues in the project during the past week
Avoidable Defects: a shortcoming, fault, imperfection or problem that could be prevented such as human error
Unavoidable Defects: a shortcoming, fault, imperfection or problem that the team has no control over such as a change in the requirement
Concern: A matter that might cause some trouble, worry or an unsettled matter is ready for a decision
A. List any avoidable defect occurred in the previous week
| Avoidable Defects | Proposed Solution
1 | People in team are not really be at the regular meeting on time. | Make the meeting information clear. So that people will know how important the meeting is.
2
3
4
5
B. List any unavoidable defect occurred in the previous week
| Unavoidable defect | Proposed Solution
1 | The team and clients have not fixed the days for Product transition. | The clients have been repeatedly inquired about this. The team is waiting for clients to give us a positive reponse.
2 | Team members will have exams. Due to this, the schedule of the meeting is hard to be made. | Start schedule early so that people can allocate schedules for the project and meeting.
3
4
5
C. List any concern occurred in the previous week
| Concerns | Proposed Solution
1 | The clients are unaware about the details how to provide the team with a Hosting Service. | The team has found some hosting services for the clients. But hosting services are not free and the client might not like that. The team has been talking to the clients about this via emails.
2 | Because our clients are USC students, they have exam and may not be available at the end of the semester which we have to send some document and schedule meeting with thems | Show them the important of the meeting and be precise so that the meeting will not take them a lot of time.
3
4
5