## SLOC
Team Number: | 1
Week: | 13
Program Size (SLOC) | Actual
Base | 5034
Added | 804
Deleted | 89
Modified | 0
Reused | 0
From COTS | 0
Total New SLOC | 5838

## Progress
Progress Description:
Describe the progress on the project during the past week, both in qualitative and quantitative.
A. | List your top priority works that must be accomplished in this week
1 | Implement unit test for the complete functionalities
2 | Transition the system
3 | Code review fixes
4 | Complete artifacts
5 | Test system on new site
6 | Train clients
7
8
B. | List dependencies or things/decision that you waiting for in this week
1 | List of names of levels used in WAT point system from client
2 | Thread categories from clients.
3 | Background image for login, registration, and about pages from clients.
4 | Logo of the system from clients.
5 | Content for "about page" from clients.
6 | Hosting server
C. | List your accomplishments from the previous week
1 | Finalize the front end part for notification system
2 | Create the admin page
3 | Implement the changes requested from client about profile page
4 | Complete 90% of the system implementation.
5 | Implement a search result page to show more search result details
6
7
D. | Report your planned and actual man-hours for each category of your work in the previous week
| Effort (Hours) | Planned | Actual
| Operational Concept Development | 10 | 2
| System and Software Requirements Development | 0 | 0
| System and Software Architecture Development | 0 | 0
| Life Cycle Planning | 10 | 4
| Feasibility Evidence Description | 5 | 2
| Quality Management | 8 | 8
| Implementation | 50 | 72
| Testing | 12 | 30
| Project Administration | 8 | 10

## Risk
Top Project Risks as of 3/18/2015
Rank |  | Risk Description | Risk Mitigation Action Items | P(L) | S(L) | RE | No. of Weeks Active
This Week | Last Week
1 | 1 | Users may prefer existing systems with similar features | Make the WAT points system as an incentive to attract users over competitors. Advertize our system to USC and users. Create surveys and evaluate users' responses. | 5 | 9 | 45 | 16
2 | 2 | The server that will be selected to host the application may encounter a performance problem as it needs to host application developed with PHP, Node.js, Redis, and Elasticsearch. | Perform testing to optimize the application and evaluate potential server candidates to suggest the clients. | 6 | 5 | 30 | 2
3 | N/A | Client may not be able to find maintainer with in the transition period | The team will provide detail user manual to the client. | 7 | 3 | 21 | 0

## COTS
List of third-party components being considered for use in the system as of 2/4/2015
Component Name | Function of the component in the system | Related components |  | Component use in the system
|  | Dependency | Interaction | Black Box | White Box | Modify Code
MySQL | Data storage for the system |  | MySql driver to interact with Web-server | x
Apache | web-server for the system |  |  | x
Jquery | DOM manipulation | Javascript |  |  | x
Bootstrap | UI library (template system) | Javascript |  |  | x
Laravel | Framework | PHP |  |  | x
TinyMCE | HTML editor for users | Javascript |  |  | x
Elasticsearch | Search system | JVM | Elasticsearch API for PHP | x
PhpUnit | Unit Test | PHP | Test the function | x
Websocket | Real-time communication between front-end and back-end | Javascript | as Node.Js Module | x
NodeJS | Javascript Server/ send data firing from back-end (in redis) and send them to the front-end by utilizing websocket module | Javascript | with Websocket and Redis | x
Redis | Receive event firing from the backend / Key-value |  | with Node.js and Websocket | x
FullCalendar | Event Plugin | Javascript, Jquery |  |  | x
Components that were filtered in the previous week
Component Name | Rationale for filtering the component |  | Notes and References

## Defects, Problems, and Concerns
Defects, Problems, and Issues
Describe the defects, problems, and issues in the project during the past week
Avoidable Defects: a shortcoming, fault, imperfection or problem that could be prevented such as human error
Unavoidable Defects: a shortcoming, fault, imperfection or problem that the team has no control over such as a change in the requirement
Concern: A matter that might cause some trouble, worry or an unsettled matter is ready for a decision
A. List any avoidable defect occurred in the previous week
| Avoidable Defects | Proposed Solution
1 | The clients were unaware of TRR review location | Team member who incharge should email, text, call, and use every means possible to remind and let them know the precise details
2 | The team should not make update to the server at the last minute. | The changes to the server should be made 24 hours prior to real-time usage. Every member should test the system and find whether the feature work properly.
3 | The Back-end and Fromt-end comment are not meaningful | The team has been notified and will work on providing meaningful code comments.
4
5
B. List any unavoidable defect occurred in the previous week
| Unavoidable defect | Proposed Solution
1 | Due to work load of other courses, planned jobs could'nt be completed. | Every members should review their schedule and try to complete their weekly assigned task.
2 | The team member should divide the task for the documents in advance to avoid last minutes pressure. | The tasks are devided, and each team member is made in-charge of a specific document.
3
4
5
C. List any concern occurred in the previous week
| Concerns | Proposed Solution
1 | The team and clients have not fixed the days for Product transition. | The clients have been asked about it. They will soon let the team know their free time and fix a day or two for the transition.
2 | The clients are unware how to provide the hosting services to the team. | The team will provide hosting service options to the clients and leave the final decision to them.
3
4
5