## SLOC
Team Number: | 1
Week: | 4
Program Size (SLOC) | Actual
Base | 0
Added | 0
Deleted | 0
Modified | 0
Reused | 0
From COTS | 0
Total New SLOC | 0

## Progress
Progress Description:
Describe the progress on the project during the past week, both in qualitative and quantitative.
A. | List your top priority works that must be accomplished in this week
1 | Demonstrate the GUI prototype to the client
2 | Finalize the Win-Win negotiations and complete the Win-Win negotiation report
3 | Discuss and Analyse the like/dislike capability algorithm with the client
4 | Finalize the GUI prototype designed
5 | Draft the Foundation Commitment Package
6 | Present you first prototype presentation in class
7 | Decide which NDI will we use to develop the project
8
B. | List dependencies or things/decision that you waiting for in this week
1 | The prototype designed is acceptable to the clients
2 | Approval of the like/dislike functionality, establish a firm understanding of the problem
3 | Detrmine if the client requires us to develop a system to redeem points
4
5
C. | List your accomplishments from the previous week
1 | Developed an graphical user interface prototype
2 | Developed the Business workflow, Result chain and program model for the project
3 | Came up with an algorithmic solution for a specific core capability
4 | Completed the initial Win-Win negotiation session
5 | Understood the necessity of developing such a system
6 | Updated the negotiated Win-Win requirements on Winbook
7 | Completed VCP package
8
D. | Report your planned and actual man-hours for each category of your work in the previous week
| Effort (Hours) | Planned | Actual
| Operational Concept Development | 28 | 31.5
| System and Software Requirements Development | 18 | 21.5
| System and Software Architecture Development | 0 | 0
| Life Cycle Planning | 4 | 3
| Feasibility Evidence Description | 4 | 5
| Quality Management | 2 | 2
| Implementation | 0 | 0
| Testing | 0 | 0
| Project Administration | 30 | 37

## Risk
Top Project Risks as of 10/01/2014
Rank |  | Risk Description | Risk Mitigation Action Items | P(L) | S(L) | RE | No. of Weeks Active
This Week | Last Week
1 | 1 | Undefined Plan and Requirements: The requirements of the system are not solid, and are just partly known. Requirement have a tendency to change when the project progresses. | Consult with the clients to find more details about the unclear features, develop the prototype or graph to clarify the features, and discuss about the potential system flaws | 9 | 9 | 81 | 2
2 | 3 | User Risk: users may not accept to use the system even if all the specification are met by the system | We need to have certain level of discussion with the actual users as to whether they are willing to learn and use the new system we are developing | 5 | 9 | 45 | 2
3 | 7 | Scope and Time constraint: The scope of this project is very large. There are many components that need to be considered. To include all functionalities client mentioned within this time constraint might not be possible | Prioritize all features and develop the most needed features first | 7 | 5 | 35 | 2
4 | 2 | Lack of Invovement by success-critical-stakeholders:Do not understand clearly enough the success-critical Stakeholder positions | Further understanding of needs and system scoping is needed | 3 | 7 | 21 | 2
5 | N/A | Client rejects our prototypes | Re-evaluating the client's requirements and establishing a new prototype according to requirements | 4 | 5 | 20 | 1
6 | 5 | Client's availability: He is extremely busy. Schedule a meeting during class schedule might not be possible | Forsee meetings in advance and acquire cilent's schedule. If there will be a meeting, the team will notify the clients early to allocate the time slot. | 4 | 4 | 16 | 2
7 | 4 | Architecture/Reuse/Non-Development Item conflict: There is no current server available for our system. The COTS/NDI used are poorly matched. A database system may be needed in order to keep the accounts, logs and forum informations | Looking for services provided only and analyze all options if they are suitable to our conditions. Establish off-line server for using as a prototype for the clients manages to overcome the problem of interoperatibility | 3 | 5 | 15 | 2
8 | N/A
9 | N/A
10 | N/A

## COTS
List of third-party components being considered for use in the system as of 10/01/2014
Component Name | Function of the component in the system | Related components |  | Component use in the system
|  | Dependency | Interaction | Black Box | White Box | Modify Code
MySQL | Data storage for the system |  | MySql driver to interact with Web-server | x
Apache | web-server for the system |  |  | x
Drupal | CMS | PHP |  |  |  | x
Joomla | CMS | PHP |  |  |  | x
Wordpress | CMS | PHP |  |  |  | x
Jquery | DOM manipulation | Javascript |  |  | x
Bootstrap | UI library (template system) | Javascript |  |  | x
Components that were filtered in the previous week
Component Name | Rationale for filtering the component |  | Notes and References
N/A | N/A |  | N/A

## Defects, Problems, and Concerns
Defects, Problems, and Issues
Describe the defects, problems, and issues in the project during the past week
Avoidable Defects: a shortcoming, fault, imperfection or problem that could be prevented such as human error
Unavoidable Defects: a shortcoming, fault, imperfection or problem that the team has no control over such as a change in the requirement
Concern: A matter that might cause some trouble, worry or an unsettled matter is ready for a decision
A. List any avoidable defect occurred in the previous week
| Avoidable Defects | Proposed Solution
1 | Problem with WinWin negotitation time slot | We should have contacted the TA earlier
2 | Concept of program model (esp. value propositions) was not clear to us | WinWin negotiation session with the TA and the client refined the program model.
3 | Uncertainties about the core features of the project among team members | Create a flowchart to clarify the features to both clients and team members
4
5
B. List any unavoidable defect occurred in the previous week
| Unavoidable defect | Proposed Solution
1 | Client came up with new features (3 WAT points system, best answer) to be considered | The feature should be negotatiated and analyzed if it is feasible or not
2 | Some of the requirements are still uncertain | Schedule another meeting with the client and come up with Win-Win negotiations
3 | Our clients are quite busy; so, it is hard to make an appointment | Making an appointment to meet with the clients early so that they can allocate time.
4
5
C. List any concern occurred in the previous week
| Concerns | Proposed Solution
1 | Having a prototype website to the test points system | Develop initial prototype and algorithm
2 | There is no specific requirements for the UI | Find out whether we can design it freely and how we should design it by consulting with the clients
3 | There is no system maintainer | The client does not require a maintainer, after the system is developed
4 | There is no budget | Analyze more options that will not cost the team money, such as open souce software and free hostings
5