## SLOC
Team Number: | 1
Week: | 10
Program Size (SLOC) | Actual
Base | 0
Added | 0
Deleted | 0
Modified | 0
Reused | 0
From COTS | 0
Total New SLOC | 0

## Progress
Progress Description:
Describe the progress on the project during the past week, both in qualitative and quantitative.
A. | List your top priority works that must be accomplished in this week
1 | Finish analyse and evaluate NDI which will use for the project
2 | Create UI mockup
3 | Continue developing system architecture
4 | Finish the Return of Investment analysis
5 | Start learning about selected NDI
6 | Conduct the survey
7 | Prepare draft DCP
8 | Plan test cases
B. | List dependencies or things/decision that you waiting for in this week
1 | Waiting for finalized version of ROI analysis feedback from clients
2 | Acquire feedback from users (survey)
3 | Make final decision about framework
4
5
C. | List your accomplishments from the previous week
1 | Received rough ROI analysis from clients
2 | Received first version of the survey feedback from clients
3 | Plan on getting information from real user via survey related to User Interface
4 | Make the schdule for coming tasks
5 | Plan and perform Prototype Presentation in class
6 | Complete the first version of the survey
7 | Review project documents
8 | Updated the FED file to V2.1
D. | Report your planned and actual man-hours for each category of your work in the previous week
| Effort (Hours) | Planned | Actual
| Operational Concept Development | 8 | 4
| System and Software Requirements Development | 4 | 0
| System and Software Architecture Development | 8 | 2
| Life Cycle Planning | 10 | 8
| Feasibility Evidence Description | 48 | 63
| Quality Management | 2 | 2
| Implementation | 0 | 0
| Testing | 0 | 0
| Project Administration | 2 | 1

## Risk
Top Project Risks as of 11/12/2014
Rank |  | Risk Description | Risk Mitigation Action Items | P(L) | S(L) | RE | No. of Weeks Active
This Week | Last Week
1 | 1 | Users may prefer existing systems with similar features | Make the WAT points system as an incentive to attract users over competitors. Advertize our system to USC and users. Create surveys and evaluate users' responses. | 7 | 10 | 70 | 2
2 | 2 | User Risk: users may not accept to use the system even if all the specification are met by the system | - We conduct the survey to acquire users' feedback regarding the project. - We will create the user interface mock up to acquire feedback from the clients | 7 | 10 | 70 | 10
3 | 2 | Lack of Involvement by success-critical-stakeholders:Do not understand clearly enough the success-critical Stakeholder positions | - Potential users will be involved via conducting a survey and by letting them test prototypes of the user interface. -Clients are involved by verifying that our work fits their expectations and by holding weekly meetings. | 5 | 10 | 50 | 10
4 | 5 | May not have sufficient time to create comprehensive prototypes for important parts of the system | Prioritize the prototyping. Use minimum effort for each prototype to gain enough information to see the feature is feasible. | 8 | 6 | 48 | 2
5 | 4 | Undefined Plan and Requirements: - The scope of the campaign functionality is not finalized - The requirement about the UI of the system is not finalized - The point system is still not verified by potential users - The scope of the search functionality is not certain Requirement have a tendency to change with project development. | - Consult with the clients how campaign functionality works - Prototyping will help us know more about point systems, search functionality, and UI - Get the feedback of surveys for UI | 5 | 9 | 45 | 10

## COTS
List of third-party components being considered for use in the system as of 11/12/2014
Component Name | Function of the component in the system | Related components |  | Component use in the system
|  | Dependency | Interaction | Black Box | White Box | Modify Code
MySQL | Data storage for the system |  | MySql driver to interact with Web-server | x
Apache | web-server for the system |  |  | x
Joomla | CMS | PHP |  |  |  | x
Jquery | DOM manipulation | Javascript |  |  | x
Bootstrap | UI library (template system) | Javascript |  |  | x
Wordpress | CMS | PHP |  |  |  | x
Magnolia | CMS | JAVA |  |  |  | x
Laravel | Framework | PHP |  |  | x
Spring | Framework | JAVA |  |  | x
JSF | Framework | JAVA |  |  | x
Cake PHP | Framework | PHP |  |  | x
Django | Framework | Python |  |  | x
Components that were filtered in the previous week
Component Name | Rationale for filtering the component |  | Notes and References

## Defects, Problems, and Concerns
Defects, Problems, and Issues
Describe the defects, problems, and issues in the project during the past week
Avoidable Defects: a shortcoming, fault, imperfection or problem that could be prevented such as human error
Unavoidable Defects: a shortcoming, fault, imperfection or problem that the team has no control over such as a change in the requirement
Concern: A matter that might cause some trouble, worry or an unsettled matter is ready for a decision
A. List any avoidable defect occurred in the previous week
| Avoidable Defects | Proposed Solution
1 | Indicisiveness about NDI usage slowing down project progress | Set stricter deadlines for individual NDI assessment to avoid delays
2 | Different understanding about the purpose of the survey between development team and clients has been slowing down project progress. | Hold a survey meeting with clients and development team to eliminate conflictions.
3 | ROI is difficult to determine | Involve the client in working out the ROI
4 | Some of the requirements are still uncertain | Schedule another meeting with the clients and discuss uncertain requirements
5
B. List any unavoidable defect occurred in the previous week
| Unavoidable defect | Proposed Solution
1 | There may not be enough time to create prototypes | Prioritize and prototype features with high risk using minimal effort for each prototype.
2
3
4
5
C. List any concern occurred in the previous week
| Concerns | Proposed Solution
1 | We need to make a decision for which framework to use, but we are not sure if it will be the best option. | Do a thorough analysis of how the selected framework meets key requirements.
2 | User feedback from the survey might not be fully reliable | Make the survey to be clear and self explainitory and let users test a realistic prototype of our user interface
3
4
5