## SLOC
Team Number: | 1
Week: | 12
Program Size (SLOC) | Actual
Base | 0
Added | 318
Deleted | 0
Modified | 0
Reused | 0
From COTS | 0
Total New SLOC | 318

## Progress
Progress Description:
Describe the progress on the project during the past week, both in qualitative and quantitative.
A. | List your top priority works that must be accomplished in this week
1 | Start learning about selected NDI
2 | Analyze the survey results
3 | Finish UI mockup
4 | Prepare draft DCP
5 | Plan test cases
6 | Complete architecture
7 | Complete draft documents
8
B. | List dependencies or things/decision that you waiting for in this week
1 | Client prototype feedback
2 | DCR ARB feedback
3
4
5
C. | List your accomplishments from the previous week
1 | Finished analysing and evaluating NDI which will use for the project
2 | Continue developing UI mockup
3 | Continue developing system architecture
4 | Finish the Return of Investment analysis
5 | Conduct the survey
6 | Continue working on ARP DCP documents
7 | Updated FED file to version 2.2
8
D. | Report your planned and actual man-hours for each category of your work in the previous week
| Effort (Hours) | Planned | Actual
| Operational Concept Development | 0 | 0
| System and Software Requirements Development | 0 | 0
| System and Software Architecture Development | 20 | 16
| Life Cycle Planning | 5 | 8
| Feasibility Evidence Description | 30 | 36
| Quality Management | 6 | 4
| Implementation | 12 | 18
| Testing | 2 | 2
| Project Administration | 6 | 4

## Risk
Top Project Risks as of 11/26/2014
Rank |  | Risk Description | Risk Mitigation Action Items | P(L) | S(L) | RE | No. of Weeks Active
This Week | Last Week
1 | 1 | Users may prefer existing systems with similar features | Make the WAT points system as an incentive to attract users over competitors. Advertize our system to USC and users. Create surveys and evaluate users' responses. | 7 | 10 | 70 | 3
2 | 2 | User Risk: users may not accept to use the system even if all the specification are met by the system | - We conduct the survey to acquire users' feedback regarding the project. - We will create the user interface mock up to acquire feedback from the clients | 7 | 10 | 70 | 11
3 | 2 | Lack of Involvement by success-critical-stakeholders:Do not understand clearly enough the success-critical Stakeholder positions | - Potential users will be involved via conducting a survey and by letting them test prototypes of the user interface. -Clients are involved by verifying that our work fits their expectations and by holding weekly meetings. | 5 | 10 | 50 | 11
4 | 5 | May not have sufficient time to create comprehensive prototypes for important parts of the system | Prioritize the prototyping. Use minimum effort for each prototype to gain enough information to see the feature is feasible. | 8 | 6 | 48 | 3
5 | 4 | Undefined Plan and Requirements: - The scope of the campaign functionality is not finalized - The requirement about the UI of the system is not finalized - The point system is still not verified by potential users - The scope of the search functionality is not certain Requirement have a tendency to change with project development. | - Consult with the clients how campaign functionality works - Prototyping will help us know more about point systems, search functionality, and UI - Get the feedback of surveys for UI | 5 | 9 | 45 | 11

## COTS
List of third-party components being considered for use in the system as of 11/26/2014
Component Name | Function of the component in the system | Related components |  | Component use in the system
|  | Dependency | Interaction | Black Box | White Box | Modify Code
MySQL | Data storage for the system |  | MySql driver to interact with Web-server | x
Apache | web-server for the system |  |  | x
Jquery | DOM manipulation | Javascript |  |  | x
Bootstrap | UI library (template system) | Javascript |  |  | x
Laravel | Framework | PHP |  |  | x
Components that were filtered in the previous week
Component Name | Rationale for filtering the component |  | Notes and References
Spring | FED rating |  | FED v2.2
JSF | FED rating |  | FED v2.2
Cake PHP | FED rating |  | FED v2.2
Django | FED rating |  | FED v2.2
Magnolia | FED rating |  | FED v2.2
Wordpress | FED rating |  | FED v2.2
Joomla | FED rating |  | FED v2.2

## Defects, Problems, and Concerns
Defects, Problems, and Issues
Describe the defects, problems, and issues in the project during the past week
Avoidable Defects: a shortcoming, fault, imperfection or problem that could be prevented such as human error
Unavoidable Defects: a shortcoming, fault, imperfection or problem that the team has no control over such as a change in the requirement
Concern: A matter that might cause some trouble, worry or an unsettled matter is ready for a decision
A. List any avoidable defect occurred in the previous week
| Avoidable Defects | Proposed Solution
1 | We spent lot of time in coming up with the survey | Should have schedule a meeting with the client earlier, and decreased the time spent by overgoing through things
2 | We spent lot of time in deciding NDI/ COTS | Should set the solid schedule for evaluate NDI and schedule the meeting to find the progress regularly, we also do not know the value of the task
3 | Team members did not have a clear understanding about what they should be doing | Make sure everybody is on the same page on tasks at hand
4
5
B. List any unavoidable defect occurred in the previous week
| Unavoidable defect | Proposed Solution
1 | There might not be enough time to prototype all essential features of the system | Prioritize and prototype features with high risk using minimal effort for each prototype.
2
3
4
5
C. List any concern occurred in the previous week
| Concerns | Proposed Solution
1 | The survey conducted may not be reliable enough to evaluate whether we should develop the project | Analyse the surveys throughly, and come up with more surveys if needed.
2 | Team members were unfimiliar with the NDI/NCS chosen for the project | Team member spent time to study each framwork before rating
3
4
5